## Open
East Craigs Parent Council
Action Number | Action | Owner | Update | Status | Due date
2016-11-01 | ECPC Secretary - Ms Reid to arrange for a wider communication to be issued to all parents to state that we are seeking a secretary for Parent Council | Senior Management Team | Mrs A.Reid has kindly offered to take notes at ECPC meetings going forward. | Closed
2016-11-03 | Language Workshops - Senior Leadership Team to privde regular updates on Language workshop / materials available to parents to support their child's learning | Senior Management Team | Mrs Donaldson is meeting with Cluster schools and information will be shared once it is available | Open
2016-11-06 | Residential Excursion - Parent Council to contact Robin Yellowlees highlightng concerns / issues regarding competitive pricing with private providers | SI/CR | Email issued from ECPC mailbox but response outstanding. We will continue to chase! Ms Reid has separately followed this up too and so has Mr Rae (Head of Craigmoung High), but no response received to date. | Open
2016-11-07 | Residential Excursion - Senior Team to establish when the September weekend is in 2018, and if this clashes with the proposed excursion dates, consider alternative dates. | Senior Management Team | Dates for 2018 residential excursion have been moved to avoid the September weekend. | Closed
2016-11-09 | Leavers' Event - Ms Reid to arrange to consult children and find out how they feel and what they would like to do. | Senior Management Team | Consulation taking place week commencing 30 January | Closed
2017-01-01 | School Lunches: Ms Reid to continue to liaise with catering manager and dining staff and monitor the situation and report back at next meeting to see if there has been an improvement. | Senior Management Team |  | Open
2017-01-02 | School Lunches - And possibly only give P1’s half a baked potato as they are not managing to eat a full one. Ms Reid to confirm whether this can be done going forward. | Senior Management Team |  | Open
2017-01-03 | School Grounds: Ms Reid to take investigate re P1 playground as the astroturf should already have been secured down. | Senior Management Team |  | Open
2017-01-04 | School Grounds - Carol Cerden (parent @ Gillespies) was involved in raising a large amount of money for the development of their playground. Ms Isler to look at different funding options by getting touch with Gillespies. | S.Isler |  | Open
2017-01-05 | School Grounds - Ms Reid to contact builders as the agreement at the outset of building work was that outdoor learning space would be reinstated. | Senior Management Team |  | Open
2017-01-06 | Lagganlia Fees - Ms Reid to speak to Ms McIntosh (in the office) regarding the best way for her to receive the payments and to then communicate this to parents. | Senior Management Team |  | Open
2017-01-07 | 1 in 5 Poverty Awareness - Meeting to be arranged with ECPC/PTA chairs to look at results to find a positive way forward in terms of calendar/subsidy of events. | Senior Management Team |  | Open
2017-01-08 | 2017/18 Class Organisation - Ms Reid to meet with Ms Rigby&Ms Isler by end of February. | Senior Management Team |  | Open
2017-01-09 | PTA Update - Request that PTA issue reminders in advance of meetings to increase their attendance and publish Minutes of their meetings via school website (PTA section) | PTA |  | Open
2017-01-10 | AOB - Reminder to be issued via Newsletter on East Craig uniform. | Senior Management Team |  | Open
2017-01-11 | AOB - Gym Hall Windows: Ms Reid to see if this can be overridden or adjusted. | Senior Management Team |  | Open

## Closed
East Craigs Parent Council
Action Number | Action | Owner | Update | Status | Due date
2015-05-1 | Raising Rolls - Parentmail link to raising rolls website to be issued | Mandy Crosbie | Issued 21 May | Closed
2015-05-4 | PTA Funds - Jackie Reid&PTA to communicate on how current funds will be used | Jackie Reid | Updated provided at AGM and per newsletter | Closed
2015-05-5 | Hoodies - School staff to feedback to PTA with their views | Jackie Reid | Zipped, grey school hoodies now available via Borders Embroidery at £11.50 | Closed
2015-05-6 | School Uniforms - PTA to look into using Tesco for embroidered clothes | Lynne Wallace | Lynne obtained information on costs as well as quality&service and PTA have come to conclusion that while items are indeed cheaper, the quality is not the same and the customer service would be missing completely. There is also the hige amount of time and effort that would be required to run both the Borders Embroidery service and getting TEsco up and running. Decision was made not to progress with this at this point in time. | Closed
2015-05-2 | Ground repairs - School to obtain 3 quotes from contractors for borders and other grounds work | Senior Management Team | Ongoing - delay due to Business Manager changeover> Nov Update - On hold until after building work on gym hall has been completed | closed
2015-05-3 | Painting Playground Games (lower playground) - Shelley to contact Fiona Kenny to check re using James / Kate who helped with murals to try and tie in designs | Senior Management Team | Ongoing - Quotes to be obtained week commencing 21 Sept - pupils will be consulted on design and outside play equipment. Nov Update - pupils consulted and outcome communicated via newsletter | closed
2015-05-7 | Sainsbury Vouchers - The Pupil Coucil would speak with classes and get ideas on how to best spend these | Senior Management Team | Ongoing Nov Update - Amount banked to be used for larger purchase next year (on cokking and sports equipment respectively) | closed
2015-09-3 | Additional Sheltered Area - Senior Team to look at options (including consideration of location of any shelter to ensure no impact on classrooms for noise and distraction as well as the overall building security) | Senior Management Team | Nov Update - no budget available via school / council funds, but application made to bid for lottery monies (up to £10K) and if monies are secured a non-permanent shelter would be built in consultation with Parents and Pupils. It would be a mulit-purpose structure that could also be used for learning, eg a stage or similar. Senior team will come back to ECPC once progress has been made in securing the funds. | closed
2015-09-2 | PE Objectives - Senior Team to clarify with Mr Chung on PE Milestones and communicate back to parents | Senior Management Team | Nov Update - Mr Chung to communicate PE Milestones Jan Update - milestones circulated&offer of education session made | Closed
2015-09-4 | Scooters / Cycles - reminder to parents&pupils re safe use and conduct of scooters / cycles on playgrounds, include in Newsletter and mention at Assemblies. | Senior Management Team | Reminder included in September Newsletter Nov Update - suggestion to put up signs both at the bike stand and perimeter fence / noticebox as a reminder of "no scooting / cycling rule on school property" Jan Update - pupils reminded via assemblies again | Closed
2015-11-01 | Recruitment Training - any volunteers to complete form to receive training | Co-Chairs | Jan Update - there are 4 parents trained at present | Closed
2015-11-03 | Parentmail - office to contact parents to register email addresses so East Craigs can run own version of parentmail | Admin Team | Jan Update - email sent asking parents to respond and new system in palce | Closed
2015-11-04 | School Bell - Ms Reid will investigate whether bell can give a warning bell 2 mins prior to 8.50 | Senior Management Team | Jan Update - this is now in practice and parents were informed of change | Closed
2015 - 11-05 | PE Kits - teachers to remind children to take kit home to be washed | Senior Management Team | Jan Update - teachers have reminded children, parents to flag if still not happening | Closed
2015 - 09-1 | P7 Leavers Dance - Senior team to speak to P7 staff and pupils to confirm date and format. | Senior Management Team | Nov Update - Discussions ongoing and to come back to a future ECPC meet | Closed
2015-09-5 | Sginatories for Account - complete changeover | Co-Chairs / Fiona Kenny | Nov Update - outstanding | Closed
2015-11-02 | Language Teaching in School - parents will get opportunity to feedback via Parent Survey | Senior Management Team | Info evening at Craigmount | Closed
2015-11-06 | Breakfast Club - allocation of spaces to be reviewed with a view to increase available spaces as demand is there | Senior Management Team | Ms Reid speaking with Jonathan at Oscars to review provision. | Closed
2016-03-01 | Senior team to arrange a workshop around Composite Class arrangements. | Senior Team | In train - arrangments being finalised and communicated shortly | Propose to close
2016-03-02 | Mrs Johnston to provide weekly updates on rising roll building progress | Ms Johnston | Ongoing updates issued | Propose to close
2016-03-03 | Senior team to consider whether a workshop on language teaching could be run once confirmation of what will be taken forward has been made (by Cluster schools / Craigmount HS) | Senior Team | Confirmation that going forward French will be taught from nursery to P7 and German introduced from P5 onwards. Staff training has been arranged for August and Senior Team looking at possibly running an information session for parents in next academic session | Propose to close
2016-03-04 | Parental Involvement requested in taking this forward. Ms Reid to send out more information in due course. | Ms Reid | Included in April Newsletter and letters issued to parents via bag drop. Session due to take place 13 May | Propose to close
2016-03-05 | Ms Reid to mention Readathon in March newsletter | Ms Reid | Done | Propose to close
2016-03-06 | Panto Trip / Christmas Outing - senior team to consider options and to canvas pupils’ opinions. | Senior Team | PTA fully funding M&M production to preform Peter Pan in school (in the new games hall) with full school attendance | Propose to close
2016-03-07 | Senior team to link with other cluster schools to see if appetite there to run a CEOPS workshop or if not, run one for East Craigs PS | Senior Team | Discussions held with other cluster heads and clear appetite to run this at cluster level for P6&P7s in the next academic session | Propose to close
2016-05-01 | Composite Class Workshop for affected parents to be set up | Senior Team | Session took place | Propose to close
2016-05-02 | To discuss option of both PTA & parent council coming together as one group and look at school which run this format | PTA | PTA meetings confirmed to run separate from ECPC | Propose to close
2016-05-03 | Gym Hall / Classroom extension: Language of workmen to be addressed | Senior Team | Done | Propose to close
2016-05-04 | ICT Provision: provision to be made for new classrooms ICT still priority in school improvement plans | Senior Team | Use of new i-pads arranged across school | Propose to close
2016-05-05 | Parentmail - easer to identify headers / subjects on emails; school office will check this when sending items out | School Office |  | Propose to close
2016-03-07 | Senior team to link with other cluster schools to see if appetite there to run a CEOPS workshop or if not, run one for East Craigs PS | Senior Team | Discussions held with other cluster heads and clear appetite to run this at cluster level for P6&P7s in the next academic session
2016-03-03 | Senior team to consider whether a workshop on language teaching could be run once confirmation of what will be taken forward has been made (by Cluster schools / Craigmount HS) | Senior Team | Confirmation that going forward French will be taught from nursery to P7 and German introduced from P5 onwards. Staff training has been arranged for August and Senior Team looking at possibly running an information session for parents in next academic session
2016-09-01 | Residential excursion to Lagganlia - To check if centre provides waterproofs & to look at fundraising to bring costs down | Senior Team
2016-09-02 | Old notice board to be taken down and enquire about a new one | Senior Team
2016-09-03 | Language Provision - contact Clermiston Primary to see what they have given out to parents | Senior Team
2016-09-04 | PTA Update - school badge to be given to Lynn | Mrs Crosby
2016-11-02 | ECPC Chair to ensure that agenda and action log have been widely circulated as very few people received them this time | SI/CR | Email reminder issued 13 Jan via school office to confirm date&ask for any agenda items. Members contacted 18 Jan with draft agenda to ask for additional items Agenda&action log issued to parent body via school office - 20 Jan | Closed
2016-11-04 | School Extention - Opening Ceremony - formal communication to be issued | Senior Management Team | Done | Closed
2016-11-05 | CEOP Meeting - Ms Reid to pass positive feedback to Police Officer who ran the session | Senior Management Team | Done | Closed
2016-11-08 | 1 in 5 poverty initiative - Ms Reid to organise a survey for parents in order to gather more feedback from a wider cross section regarding "reducing the cost of the school day" strategies. | Senior Management Team | Survey issued - closing date 20 January | Closed